## Task List Fabio
TASK LIST SOFTWARE ENGINEERING Groep-10: <name:nr> |  |  |  |  | Fabio Puissant - 2055346
TASK | PRIORITY | STATUS | START DATE | DUE DATE | HOURS WORKED | NOTES | TOTAL HOURS OF EFFORT
Eerste meeting | High | Complete | 2020-10-16 | 2020-10-16 | 3 | Taakverdeling, kennismaking, communicatie kanalen afgersproken | 23
Fysieke Meeting | High | Complete | 2020-10-22 | 2020-10-22 | 3 | Projectvoorstellen besproken, taakverdeling
Project tutors analyse | Normal | Complete | 2020-10-22 | 2020-10-24 | 2.5 | project omschrijving en URPS
Digitale meeting Dave | High | Complete | 2020-10-24 | 2020-10-24 | 1 | project tutors evaluatie
Project tutors analyse | Normal | In Progress | 2020-10-24 | 2020-10-30 | 0.5 | Kritiek implementreren
Project tutors presentatie | Normal | In Progress | 2020-10-26 | 2020-10-30 | 3 | Maken van de presentatie versie 1 + Effort Analyse
Project Puntensysteem | High | Complete | 2020-10-29 | 2020-10-29 | 1 | URPS omschreven voor dit projectvoorstel
Digital Meeting team | High | Complete | 2020-10-30 | 2020-10-30 | 1.5 | Project analyses, mock ups, URPS geëvalueerd+ taakverdeling tegen volgende meeting 1/11/2020
Opstellen log bestand Excell | High | Complete | 2020-10-30 | 2020-10-30 | 1.5 | Log bestand voor uren-taak logging in Excel
Presentatie tutoren | High | Complete | 2020-10-31 | 2020-10-31 | 0.5 | kritiek implementeren
Presentatie oefenen in team | Normal | Complete | 2020-11-04 | 2020-11-04 | 1.5 | presentatie in team oefenen
Presentatie geven | Normal | Complete | 2020-11-04 | 2020-11-04 | 0.5 | Presentatie geven op punten
Meeting team na presentatie voor feedback | Normal | Complete | 2020-11-04 | 2020-11-04 | 1 | Scope herbepalen, verlengen van het veeteelt project
Meeting team taakverdeling en use cases | Normal | Complete | 2020-11-06 | 2020-11-04 | 1 | Brainstormen de nieuwe > scope, rollen, taken en use cases noteren voor de uitgebreide scope veeteelt
| Normal | Complete | 2020-11-04 | 2020-11-04 | 1.5

## Task List Wouter
TASK LIST SOFTWARE ENGINEERING Groep-10: <name:nr>
TASK | PRIORITY | STATUS | START DATE | DUE DATE | HOURS WORKED | NOTES | TOTAL HOURS OF EFFORT
First thing I need to do | Normal | Not Started | 2020-11-10 | 2020-11-17 | 1 |  | 106
Other thing I need to finish | High | In Progress | 2020-10-11 | 2020-11-15 | 5
Something else to do | Low | Complete | 2020-10-18 | 2020-10-28 | 100
Formulas:
DUE DATE = ToDoList2[[#This Row],[START DATE ]]+7

## Task List Niels
TASK LIST SOFTWARE ENGINEERING Groep-10: <name:nr>
TASK | PRIORITY | STATUS | START DATE | DUE DATE | HOURS WORKED | NOTES | TOTAL HOURS OF EFFORT
First thing I need to do | Normal | Not Started | 2020-11-10 | 2020-11-17 | 1 |  | 106
Other thing I need to finish | High | In Progress | 2020-10-11 | 2020-11-15 | 5
Something else to do | Low | Complete | 2020-10-18 | 2020-10-28 | 100
Formulas:
DUE DATE = ToDoList3[[#This Row],[START DATE ]]+7

## Task List Dave
TASK LIST SOFTWARE ENGINEERING Groep-10: <name:nr>
TASK | PRIORITY | STATUS | START DATE | DUE DATE | HOURS WORKED | NOTES | TOTAL HOURS OF EFFORT
First thing I need to do | Normal | Not Started | 2020-11-10 | 2020-11-17 | 1 |  | 106
Other thing I need to finish | High | In Progress | 2020-10-11 | 2020-11-15 | 5
Something else to do | Low | Complete | 2020-10-18 | 2020-10-28 | 100
Formulas:
DUE DATE = ToDoList34[[#This Row],[START DATE ]]+7